## Rollout by Phase
Ather — AI chat rollout: customer capability by phase
Each column = the full support stack a customer has per channel × stage at that phase. Green = capability introduced or changed vs the prior phase. As of Jun 2026.
Phase Details | Phase | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
| Phase Name | Today / Status Quo | Live Agent on WhatsApp | Post-Ownership AI Bot on App (V1) | Post-Ownership on WhatsApp (→ App bot) | Pre-Ownership AI Bot on WhatsApp | Mobile Web → WhatsApp redirect | Live Agent on App (selected tickets) | Pre-Ownership AI Bot on App | Pre + Post AI Bot on Desktop Web
| Phase Description | Baseline support across App, Web and Call. WhatsApp chat dead-ends — no bot, no agent. | Introducing live chat agent support on WhatsApp – both postOwnership (P1) and preOwnership (P2). | Launch in-App AI chatbot for post-ownership support, replacing the dead-end WhatsApp chat. Targets −20% post-ownership tickets & calls. | Route WhatsApp post-ownership chats into the proven App bot rather than building a new one. Targets −20% post-ownership tickets. | Launch pre-sales / enquiry AI chatbot on WhatsApp. Targets −10% pre-ownership tickets. | Redirect all Mobile Web chats (pre, post, live agent) to WhatsApp instead of building a dedicated Mobile Web bot. | Add human live-agent handoff inside the App for selected complex post-ownership tickets. | Launch in-App pre-sales AI chatbot, replacing the dead-end WhatsApp chat for pre-ownership. | Launch web AI chatbot covering pre and post on Desktop Web. Targets −15% pre / −20% post tickets.
| Targeted Go Live Date | — | July 2026 | Aug 2026 | Nov 2026 | Feb 2027 | 2027 (H1) | 2027 | 2027 | 2027 (H2)
| Phase Prioritisation Rationale | Zero customer support provided on WhatsApp today since we have removed the Yellow AI-powered chatbot plus live agent capability. | Re-establish a human channel first — the escalation backbone every later bot hands off to. No deflection is safe without a human fallback. | App is ~51% of contacts and post-ownership is the largest volume — the single biggest deflection lever, fastest payback. | WhatsApp post-sale volume doesn't justify a separate bot; reuse the now-stable App bot for near-zero marginal effort. | WhatsApp is the natural top-of-funnel enquiry channel; pre-sales deflection follows once post-ownership coverage is solid. | Thin Mobile Web chat volume — a near-free coverage win once WhatsApp covers all three stages. | ~33% of post-sale cases always need a human; layered on after App bot maturity to handle the un-automatable residual. | Captures in-App pre-purchase intent; lower priority than post-sale and smaller than WhatsApp's top-of-funnel. | Desktop Web is the smallest contact share — lowest ROI, sequenced last after mobile-first channels.
Customer / Business Impact | Mobile App – Post Ownership support | FAQs, Chat → WhatsApp (DeadEnd), Raise a Ticket, Call, RSA | FAQs, Chat → WhatsApp (DeadEnd), Raise a Ticket, Call, RSA | FAQs, AI Chatbot (in-App, Post), Raise a Ticket, Call, RSA | FAQs, AI Chatbot (in-App, Post), Raise a Ticket, Call, RSA | FAQs, AI Chatbot (in-App, Post), Raise a Ticket, Call, RSA | FAQs, AI Chatbot (in-App, Post), Raise a Ticket, Call, RSA | FAQs, AI Chatbot (in-App, Post) → Live Agent (selected), Raise a Ticket, Call, RSA | FAQs, AI Chatbot (in-App, Post) → Live Agent (selected), Raise a Ticket, Call, RSA | FAQs, AI Chatbot (in-App, Post) → Live Agent (selected), Raise a Ticket, Call, RSA
| Mobile App – Pre Ownership support | FAQs, Chat → WhatsApp (DeadEnd), Raise a Ticket, Call | FAQs, Chat → WhatsApp (DeadEnd), Raise a Ticket, Call | FAQs, Chat → WhatsApp (DeadEnd), Raise a Ticket, Call | FAQs, Chat → WhatsApp (DeadEnd), Raise a Ticket, Call | FAQs, Chat → WhatsApp (DeadEnd), Raise a Ticket, Call | FAQs, Chat → WhatsApp (DeadEnd), Raise a Ticket, Call | FAQs, Chat → WhatsApp (DeadEnd), Raise a Ticket, Call | FAQs, AI Chatbot (in-App, Pre), Raise a Ticket, Call | FAQs, AI Chatbot (in-App, Pre), Raise a Ticket, Call
| Mobile App – Live Agent | NA | NA | NA | NA | NA | NA | Yes (selected tickets) | Yes (selected tickets) | Yes (selected tickets)
| WhatsApp – Post Ownership support | NA | NA | NA | FAQs, AI Chatbot (→ App bot, Post), Raise a Ticket, Call, RSA | FAQs, AI Chatbot (→ App bot, Post), Raise a Ticket, Call, RSA | FAQs, AI Chatbot (→ App bot, Post), Raise a Ticket, Call, RSA | FAQs, AI Chatbot (→ App bot, Post), Raise a Ticket, Call, RSA | FAQs, AI Chatbot (→ App bot, Post), Raise a Ticket, Call, RSA | FAQs, AI Chatbot (→ App bot, Post), Raise a Ticket, Call, RSA
| WhatsApp – Pre Ownership support | NA | NA | NA | NA | FAQs, AI Chatbot (Pre), Raise a Ticket, Call | FAQs, AI Chatbot (Pre), Raise a Ticket, Call | FAQs, AI Chatbot (Pre), Raise a Ticket, Call | FAQs, AI Chatbot (Pre), Raise a Ticket, Call | FAQs, AI Chatbot (Pre), Raise a Ticket, Call
| WhatsApp – Live Agent | NA | Yes (Pre & Post Ownership) | Yes (Pre & Post Ownership) | Yes (Pre & Post Ownership) | Yes (Pre & Post Ownership) | Yes (Pre & Post Ownership) | Yes (Pre & Post Ownership) | Yes (Pre & Post Ownership) | Yes (Pre & Post Ownership)
| Mobile Web – Post Ownership support | FAQs, Raise a Ticket, Call | FAQs, Raise a Ticket, Call | FAQs, Raise a Ticket, Call | FAQs, Raise a Ticket, Call | FAQs, Raise a Ticket, Call | FAQs, Chat → WhatsApp, Raise a Ticket, Call | FAQs, Chat → WhatsApp, Raise a Ticket, Call | FAQs, Chat → WhatsApp, Raise a Ticket, Call | FAQs, Chat → WhatsApp, Raise a Ticket, Call
| Mobile Web – Pre Ownership support | FAQs, Raise a Ticket, Call | FAQs, Raise a Ticket, Call | FAQs, Raise a Ticket, Call | FAQs, Raise a Ticket, Call | FAQs, Raise a Ticket, Call | FAQs, Chat → WhatsApp, Raise a Ticket, Call | FAQs, Chat → WhatsApp, Raise a Ticket, Call | FAQs, Chat → WhatsApp, Raise a Ticket, Call | FAQs, Chat → WhatsApp, Raise a Ticket, Call
| Mobile Web – Live Agent | NA | NA | NA | NA | NA | Yes (via WhatsApp) | Yes (via WhatsApp) | Yes (via WhatsApp) | Yes (via WhatsApp)
| Desktop Web – Post Ownership support | FAQs, Raise a Ticket, Call | FAQs, Raise a Ticket, Call | FAQs, Raise a Ticket, Call | FAQs, Raise a Ticket, Call | FAQs, Raise a Ticket, Call | FAQs, Raise a Ticket, Call | FAQs, Raise a Ticket, Call | FAQs, Raise a Ticket, Call | FAQs, AI Chatbot (Web, Post), Raise a Ticket, Call
| Desktop Web – Pre Ownership support | FAQs, Raise a Ticket, Call | FAQs, Raise a Ticket, Call | FAQs, Raise a Ticket, Call | FAQs, Raise a Ticket, Call | FAQs, Raise a Ticket, Call | FAQs, Raise a Ticket, Call | FAQs, Raise a Ticket, Call | FAQs, Raise a Ticket, Call | FAQs, AI Chatbot (Web, Pre), Raise a Ticket, Call
Desktop Web – Live Agent | bar: 0 to 8